## Gantt Chart
MPhil Gantt Chart: Ordinal SuStaIn for EDS-POTS-MCAS
Deadline: 1 June 2026 (FIRM) ¦ Primary: Synthetic Data ¦ Secondary: DICE Real Data (conditional on approvals)
Phase | Task | Owner | Deliverable | Start | End | W1 27/01 | W2 03/02 | W3 10/02 | W4 17/02 | W5 24/02 | W6 03/03 | W7 10/03 | W8 17/03 | W9 24/03 | W10 31/03 | W11 07/04 | W12 14/04 | W13 21/04 | W14 28/04 | W15 05/05 | W16 12/05 | W17 19/05 | W18 26/05 | W19 02/06 | W20 09/06 | W21 16/06 | W22 23/06
PHASE 1: Ethics & Setup | LREC initial submission ✓ |  | DONE - feedback received | 27/01 | 23/02
| DPO/DPIA submission ✓ | A | DONE - awaiting number | 27/01 | 02/02
| GPU implementation | A | Works but needs batching | 27/01 | 02/02
| Synthetic data v2 design ✓ | A | DONE - no hidden subtypes | 27/01 | 02/02
| Generate DICE-like synthetic ✓ | A | DONE - 5000 patients | 03/02 | 09/02
| Run SuStaIn validation ✓ | A | DONE - null test passed | 03/02 | 09/02
| Identify target journal | A | Recovery metrics | 03/02 | 09/02
| ◆ GO/NO-GO #1 | Pre-specified criteria test | PASSED (d=0.27 < 0.5) | 03/02 | 09/02
◆ GO/NO-GO #1 | Noise-free >95% recovery |  | DECISION | 03/02 | 09/02
| Generate 10% noise synthetic | A | CSV + code | 10/02 | 16/02
| Generate DICE-realistic synthetic | A | CSV + distributions | 10/02 | 16/02
| Draft revised research proposal | A | Single research question | 10/02 | 16/02
| Run SuStaIn DICE-realistic | A | Results N=2,3,4 | 17/02 | 23/02
| 5-fold CV on synthetic | A | CV metrics | 17/02 | 23/02
| Supervisor feedback on proposal | K/W | Written feedback | 17/02 | 23/02
◆ GO/NO-GO #2 | Stable interpretable subtypes |  | DECISION | 17/02 | 23/02
PHASE 2: Core Analysis |  |  |  | 24/02 | 20/04
| Final synthetic dataset (N=2000+) | A | Production dataset | 24/02 | 02/03
| SuStaIn fitting N=2,3,4,5 | A | Model outputs | 24/02 | 02/03
| Model selection (CVIC/BIC) | A | Optimal N selected | 03/03 | 09/03
| Subtype characterisation | A | Progression sequences | 03/03 | 09/03
| 10-fold cross-validation | A | Stability metrics | 10/03 | 16/03
| Bootstrap stability (500 iter) | A | Cluster stability | 10/03 | 16/03
| Draft Results section | A | Results draft | 10/03 | 16/03
◆ GO/NO-GO #3 | CV stability >0.7 |  | DECISION | 10/03 | 16/03
| Benchmark comparisons | A | K-means, RF tables | 17/03 | 23/03
| SHAP analysis | A | Feature importance | 17/03 | 23/03
BUFFER | Address feedback / iteration | A | Revised results | 24/03 | 30/03
DICE (CONDITIONAL) | DPO number received |  |  | 03/02 | 14/02
| LREC resubmission approved |  |  | 17/02 | 28/02
| Submit DICE application |  |  | 03/03 | 09/03
| DICE approval (4-6 weeks) |  |  | 10/03 | 20/04
| Est. EDS Soc approval |  |  | 24/03 | 30/03
| Est. data transfer |  |  | 31/03 | 06/04
◆ GO/NO-GO #4 | Real data received? |  | DECISION | 31/03 | 06/04
| Data cleaning (if received) | A | Clean dataset | 31/03 | 13/04
| Run SuStaIn on DICE | A | Real data subtypes | 07/04 | 20/04
◆ GO/NO-GO #5 | Include real data? |  | DECISION | 14/04 | 20/04
PHASE 3: Validation |  |  |  | 21/04 | 18/05
| Bootstrap stability (1000 iter) | A | Final stability | 21/04 | 27/04
| Sensitivity: noise levels | A | 5/15/20% noise | 21/04 | 27/04
| Sensitivity: sample size | A | Minimum N | 21/04 | 27/04
| Sensitivity: missing data | A | MCAR/MAR/MNAR | 28/04 | 04/05
| Sensitivity: biomarkers | A | Leave-one-out | 28/04 | 04/05
| Final figures and tables | A | All visualisations | 05/05 | 11/05
| Complete Results section | A | Final Results | 05/05 | 11/05
| Draft Discussion | A | Discussion draft | 05/05 | 18/05
| Supervisor review (full draft) | K/W | Comprehensive feedback | 12/05 | 18/05
◆ GO/NO-GO #6 | Draft approved? |  | DECISION | 12/05 | 18/05
PHASE 4: Writing |  |  |  | 19/05 | 29/06
| Address supervisor feedback | A | Revised draft | 19/05 | 25/05
| Finalise supplementary | A | Appendices complete | 19/05 | 25/05
| Second supervisor review | K/W | Final feedback | 26/05 | 01/06
| Reference checking | A | Citations verified | 26/05 | 01/06
| Format to UCL guidelines | A | Formatted thesis | 26/05 | 01/06
| Final revisions | A | Near-final thesis | 02/06 | 08/06
| Proofreading | A | Error-free doc | 02/06 | 08/06
| GitHub finalisation | A | Code complete | 02/06 | 08/06
| Final supervisor sign-off | K/W | Approval | 09/06 | 15/06
BUFFER | Emergency revisions | A | Final corrections | 16/06 | 29/06
★ SUBMISSION | Thesis submitted | A | COMPLETE | 23/06 | 29/06
LEGEND:
| Phase 1: Ethics & Setup |  | Phase 2: Core Analysis |  | Phase 3: Validation |  | Phase 4: Writing
| DICE (Conditional) |  | Go/No-Go Decision |  | Buffer |  | Milestone
GO/NO-GO DECISION CRITERIA: |  |  | Pre-specified criteria reject artefacts | PASSED (d=0.27) | N/A
Decision | Criteria | GO | Bootstrap ARI ≥ 0.6 (100 samples) | Proceed to main analysis | Reduce subtypes
#1 (W2) | Noise-free >95% subtype recovery | Proceed to noisy data | Cohen's d ≥ 0.5 on ≥3 domains | Proceed to validation | Methodological only
#2 (W4) | Stable interpretable subtypes | Proceed to main analysis | Reassess methodology
#3 (W7) | CV stability >0.7 | Proceed to validation | Simplify model
#4 (W10) | Real data received | Parallel real analysis | Synthetic-only thesis
#5 (W12) | Real analysis complete | Include real data | Synthetic-only thesis
#6 (W16) | Draft approved by supervisors | Final revisions | Emergency revision
SUPERVISOR MEETINGS (materials 48h prior):
30 Jan | Gantt, synthetic plan, GPU docs |  | 13 Feb | Noise-free results, journal
27 Feb | Realistic synthetic, proposal |  | 13 Mar | CV results, Results outline
27 Mar | Benchmarks, SHAP |  | 10 Apr | Full Results draft
24 Apr | Sensitivity plan |  | 8 May | Discussion draft
STATUS AS OF 27 JAN 2026: | Complete thesis draft |  | 5 Jun | Near-final thesis
✓ LREC submitted ¦ ✓ DPO/DPIA submitted ¦ ✓ Synthetic v2 ¦ ✓ MCMC fix ¦ ✓ Null test passed
⚠ GPU: works correctly but slower due to per-iteration overhead; needs MCMC batching (future work)
KEY CONTRIBUTION: MCMC reproducibility fix; GPU optimisation is future work